## NZ Sports Data Tracker
🇳🇿 New Zealand Sports Data Sources — Integration Tracker (Updated: missing datasets added)
🔴 Red rows = Blocked ¦ 🟡 Yellow = Status mismatch / incomplete ¦ 🟠 Orange = Missing dataset (newly added) ¦ 🟢 Green = Completed
# | Source Name | Category | Sport / Domain | Access Type | URL / Endpoint | Cost | Status | Priority | Assigned To | Date Started | Date Completed | Notes | Data Format | Action / Fix
1 | Active NZ Survey — Excel data tables (2017–2024) | Participation | Sport NZ | Excel Download | https://sportnz.org.nz/research-and-insights/surveys-and-data/active-nz/ | Free | ⚠ Incomplete | High |  |  |  | Gone through the page but the actual Excel files have NOT been downloaded or loaded into DB yet. | Excel (.xlsx) | Download all year tabs (2017–2024) from the page → load into pipeline as source tables
2 | Active NZ Participation Trends 2017–2023 (PDF + Excel tables) | Participation | Sport NZ | Excel Download | https://sportnz.org.nz/media/lupchbdk/active-nz-participation-trends-2017-2023_july-2024.pdf | Free | Completed | High |  |  |  | Downloaded. PDF has bar charts; companion Excel has raw tables. | PDF + Excel | Extract data tables from Excel companion file into DB
3 | Sport NZ Insights Tool (Power BI dashboard) | Participation | Sport NZ | Browser (Power BI) | https://sportnz.org.nz/resources/data-visualisation-tool/ | Free | Completed | Medium |  |  |  | Gone through all views. Stored relevant metrics in DB. | Power BI embed | Use as reference benchmark — compare your outputs to this dashboard
4 | Voice of Participant Survey | Participation | Sport NZ | Excel Download | https://sportnz.org.nz/research-and-insights/surveys-and-data/voice-of-participant/ | Free | Blocked | Medium |  |  |  | 404 Page not found on old URL. | Excel (.xlsx) | Try: https://sportnz.org.nz/research-and-insights/surveys-and-data/ and look under 'Voice of Participant'. Page may have been restructured.
5 | Voice of Rangatahi Survey (youth / schools) | Participation | Sport NZ | Excel Download | https://sportnz.org.nz/research-and-insights/surveys-and-data/voice-of-rangatahi/ | Free | Blocked | Medium |  |  |  | 404 Page not found on old URL. | Excel (.xlsx) | Try: https://sportnz.org.nz/research-and-insights/surveys-and-data/ — look under 'Youth' or email activenz@sportnz.org.nz to request the Excel directly.
6 | data.govt.nz — CKAN API | Govt Open Data | Government NZ | REST API | https://data.govt.nz/api/3/action/package_search?q=sport | Free | Blocked | High |  |  |  | 404 on current URL — CKAN endpoint has moved. | JSON | Use correct endpoint: https://catalogue.data.govt.nz/api/3/action/package_search?q=sport (note: 'catalogue' subdomain)
7 | Stats NZ — Cultural & Recreational Activities | Govt Open Data | Government NZ | REST API + CSV | https://api.stats.govt.nz/opendata/v1/Infoshare | Free | Blocked | High |  |  |  | 502 Bad Gateway. The Infoshare REST API requires a free API key registration. | JSON / CSV | Register at: https://api.stats.govt.nz — get free key → use https://api.stats.govt.nz/opendata/v1/Infoshare?subject=Sport. Alternatively use https://infoshare.stats.govt.nz/ for direct browser download.
8 | Stats NZ Infoshare API | Govt Open Data | Government NZ | REST API | https://api.stats.govt.nz/opendata/v1/Infoshare | Free (API key) | Blocked | High |  |  |  | 502 Bad Gateway. API key missing — free registration required first. | JSON | Same fix as above — register at api.stats.govt.nz for free key. Then test: GET /opendata/v1/Infoshare with Authorization header.
9 | Figure.NZ — NZ sport & recreation charts | Govt Open Data | Government NZ | CSV Download | https://figure.nz | Free | Completed | Medium |  |  |  | Downloaded a large amount of data. | CSV | Catalogue which Figure.NZ charts were downloaded — note dataset names and topics covered for pipeline mapping.
10 | Ministry of Health — Physical activity data | Govt Open Data | Government NZ | Excel Download | https://www.health.govt.nz/nz-health-statistics/health-statistics-and-data-sets/physical-activity-data-and-stats | Free | Completed | Medium |  |  |  | Downloaded Excel and CSV files. | Excel (.xlsx) | Load into DB. Check you have: obesity rates, sedentary behaviour, % meeting activity guidelines — all by region/ethnicity.
11 | World Rugby API — All Blacks results & rankings | Rugby | All Blacks / Rugby | REST API | https://api.worldrugby.org/v1/teams/1151/results | Free tier | Blocked | High |  |  |  | Site not found on this endpoint URL. | JSON | Register at: https://developer.world.rugby — free tier available. Alternatively scrape from: https://www.espn.com/rugby/team/results/_/id/133 (All Blacks on ESPN)
12 | ESPN / Opta — Super Rugby Pacific stats (scrape) | Rugby | Super Rugby | Web Scrape | https://www.espn.com/rugby/standings/_/league/270557 | Free | Completed | Medium |  |  |  | HTML page scraped. Normal standings data visible. | HTML / pandas | Parse with pandas.read_html() — extract team, played, won, lost, points. Also scrape fixtures page for match results.
13 | Rugby Reference — All Blacks historical test data | Rugby | All Blacks | Web Scrape | https://www.rugbyreference.com/national-teams/new-zealand | Free | Blocked | Medium |  |  |  | Site unreachable — domain may be down or geo-blocked. | HTML / pandas | Alternative: Use https://www.ultimaterugby.com/new-zealand/results or ESPN All Blacks results page. Also try https://www.rugby-reference.com (different domain).
14 | Opta / Statsperform — Official NZR data partner | Rugby | All Blacks / Super Rugby | Enterprise API | https://www.statsperform.com | Paid | Not Started | Low |  |  |  | Enterprise/paid — not yet explored. | JSON (enterprise) | Skip for now. Only needed if you get budget/contract. All free alternatives for All Blacks & Super Rugby data are sufficient for Sport NZ insights.
15 | ESPNcricinfo Statsguru — NZ Black Caps | Cricket | Black Caps | Python Library + Scrape | https://stats.espncricinfo.com/ci/engine/stats/index.html | Free | Blocked | High |  |  |  | Can't find NZ-specific Excel on the site. Statsguru is a dynamic query tool, not a direct download. | CSV / DataFrame | Use Python: pip install cricketdata → from cricketdata import fetch_cricinfo_statsguru. Or use Statsguru URL builder: https://stats.espncricinfo.com/ci/engine/stats/index.html?team=5 (NZ team ID=5)
16 | CricAPI via RapidAPI — live NZ cricket | Cricket | Black Caps | REST API | https://rapidapi.com/cricketapilive/api/cricbuzz-cricket | Free tier (100/day) | Blocked | High |  |  |  | Can't find a working free NZ cricket API. | JSON | Alternative: Use https://cricapi.com (free tier, 100 calls/day) or https://api.cricket.com.au is for AUS. Best free option: https://www.cricbuzz.com/api — requires RapidAPI signup. Also try cricsheet.org for free NZ match ball-by-ball CSV.
17 | NZ Cricket official site — fixtures & squads | Cricket | Black Caps / Domestic | Web Scrape | https://www.nzc.nz/black-caps/matches | Free | Blocked | Medium |  |  |  | Static web page with no structured data visible. | HTML / BeautifulSoup | Use BeautifulSoup: the page is JavaScript-rendered — try requests-html or Selenium. Or use ESPN NZ Cricket page: https://www.espncricinfo.com/series/new-zealand-matches which has scrapable HTML tables.
18 | OFC / football-data.org — All Whites & Football Ferns | Football | All Whites / Football Ferns | REST API | https://api.football-data.org/v4/teams/73/matches | Free | Blocked | Medium |  |  |  | Resource restricted — NZ team data requires Tier 2+ subscription on football-data.org. | JSON | Free alternative: Use API-Football (RapidAPI) free tier — GET /fixtures?team=2779 (NZ All Whites ID). Or scrape: https://www.transfermarkt.com/neuseeland/ergebnisse/verein/5428
19 | NZ Football National League (scrape) | Football | NZ domestic | Web Scrape | https://www.nzfootball.co.nz/competitions | Free | Blocked | Low |  |  |  | No structured data — site loads dynamically. | HTML / pandas | Try pandas.read_html() on: https://www.nzfootball.co.nz/competitions/national-league/standings. If JS-rendered, use Selenium. Low priority — focus on participation data first.
20 | Wellington Phoenix — API-Football (A-League) | Football | Wellington Phoenix | REST API | https://v3.football.api-sports.io/fixtures?league=188&team=1006 | Free tier | Blocked | Medium |  |  |  | No API key set up yet. | JSON | Register free at: https://dashboard.api-football.com — 100 calls/day free. Use league=188 (A-League), team=1006 (Wellington Phoenix). Header: X-RapidAPI-Key: YOUR_KEY
21 | 🆕 NZDep2018 Deprivation Index by Meshblock | Govt Open Data | NZ Population | Excel Download | https://www.otago.ac.nz/wellington/departments/publichealth/research/hirp/otago020194.html | Free | Not Started | High |  |  |  | NOT IN ORIGINAL TRACKER. Required to map deprivation quintiles per area — core dimension in Sport NZ Insights Tool. | Excel (.xlsx) | Download Excel from Otago Uni URL above. Contains NZDep2018 score + quintile for every meshblock in NZ. Join to Stats NZ geography via meshblock code.
22 | 🆕 Active NZ Small-Area Modelled Estimates (TA level) | Participation | Sport NZ | Email Request | mailto:activenz@sportnz.org.nz | Free | Not Started | High |  |  |  | NOT IN ORIGINAL TRACKER. The Insights Tool uses small-area modelled participation estimates at Territorial Authority (TA) level — these are not in the public Excel downloads. | Excel (.xlsx) | Email activenz@sportnz.org.nz — request modelled TA-level Active NZ participation estimates. Explain you are building a regional insights tool. Sport NZ shares these with sector partners.
23 | 🆕 MoH NZ Health Survey — Sedentary Behaviour & BMI tables | Govt Open Data | Health | Excel Download | https://www.health.govt.nz/nz-health-statistics/health-statistics-and-data-sets/nz-health-survey-annual-data-explorer | Free | Not Started | High |  |  |  | NOT IN ORIGINAL TRACKER. The MoH download already done only covered physical activity. Sedentary behaviour and BMI/obesity by region/ethnicity are separate tables needed for the Health layer. | Excel (.xlsx) | Go to NZ Health Survey Annual Data Explorer above → download additional tables: Sedentary behaviour, Overweight/obese adults by region and ethnicity. These are separate from the physical activity tables already downloaded.
24 | 🆕 Nielsen Research — Sport/Recreation Attitudes (Sector login) | Govt Open Data | Health / Attitudes | Restricted (Sector login) | https://www.sporttutor.nz/pages/description.jsf?menuId=1106 | Free (sector login) | Not Started | Medium |  |  |  | NOT IN ORIGINAL TRACKER. Nielsen attitude/motivation data is only visible inside the Sport NZ Insights Tool after completing the 30-min SportTutor training module. | Power BI / CSV | Complete free 30-min module at sporttutor.nz (link above). Once done, the restricted tier of the Insights Tool unlocks — you can view and screenshot/extract Nielsen data on sport motivations by demographic.
25 | 🆕 School Sport NZ Census — Student participation by sport | Schools | NZ Schools | CSV / Excel (contact) | https://www.schoolsport.nz/ | Free (contact) | Not Started | High |  |  |  | NOT IN ORIGINAL TRACKER. The Schools layer of the Insights Tool is powered by the School Sport NZ Census — student sport participation numbers by sport, school, and region. | Excel (.xlsx) | Contact schoolsport.nz directly for data access. Also check: https://sportnz.org.nz/research-and-insights/participation-data-and-tools/ under 'School Sport NZ Census' for any public summary Excel.
26 | 🆕 Ministry of Education — School Directory CSV | Schools | NZ Schools | CSV Download | https://www.educationcounts.govt.nz/find-school | Free | Not Started | High |  |  |  | NOT IN ORIGINAL TRACKER. School name, region, type (primary/secondary), decile/equity index. Required to join School Sport data to geography. | CSV | Go to educationcounts.govt.nz → Find a School → Download full directory CSV. Or direct: https://www.educationcounts.govt.nz/statistics/schooling/student-numbers — look for 'School directory' CSV download link.
27 | 🆕 Ministry of Education — Student Enrolments by Ethnicity | Schools | NZ Schools | CSV Download | https://www.educationcounts.govt.nz/statistics/schooling/student-numbers | Free | Not Started | High |  |  |  | NOT IN ORIGINAL TRACKER. Student counts by school, year level, and ethnicity — needed to contextualise school sport participation data by demographic. | CSV | educationcounts.govt.nz → Statistics → Schooling → Student Numbers → download 'School roll by ethnicity' CSV. Updated annually.

## ⚠ Missing Datasets
⚠ Datasets Missing From Your Original Tracker — Act on These First
These 7 datasets were identified as required by the Sport NZ Insights Tool but were not in your original tracker. All are FREE.
# | Dataset | Why It's Critical | Where to Get It | Format | Priority
1 | Active NZ Excel — actual data NOT yet downloaded | Marked Completed in tracker but notes say 'not downloaded yet'. The 7 years of participation data are the CORE of the Insights Tool. | sportnz.org.nz → Research → Active NZ → download all year Excel tabs (2017, 2018, 2019, 2021, 2022, 2023, 2024/25) | Excel (.xlsx) | 🔴 Critical
2 | NZDep2018 Deprivation Index by meshblock | The Insights Tool filters ALL data by deprivation quintile. Without this you can't replicate the equity analysis. | otago.ac.nz/wellington/departments/publichealth/research/hirp/otago020194.html — free Excel download | Excel (.xlsx) | 🔴 Critical
3 | Active NZ small-area modelled estimates (TA level) | The Tool shows participation data at local TA level — this is only possible with modelled small-area estimates, not raw survey data. | Email activenz@sportnz.org.nz requesting modelled TA-level estimates — free for sector partners | Excel (.xlsx) | 🔴 Critical
4 | MoH NZ Health Survey — Sedentary Behaviour & BMI tables | MoH physical activity data was downloaded but the Health layer also needs obesity/BMI and sedentary behaviour tables (separate files). | health.govt.nz → NZ Health Survey Annual Data Explorer → download Sedentary behaviour + Overweight/obese tables | Excel (.xlsx) | 🟠 High
5 | Nielsen Research — Sport/Recreation Attitudes | Restricted sector data visible inside Insights Tool after free 30-min SportTutor training. Covers motivations and barriers. | sporttutor.nz — complete free 30-min module to unlock restricted tier of Insights Tool | Power BI | 🟡 Medium
6 | School Sport NZ Census | The Schools layer of the Tool is powered by this census. Without it you cannot replicate the schools participation view. | schoolsport.nz — contact directly for data access, or check sportnz.org.nz/research-and-insights | Excel (.xlsx) | 🔴 Critical
7 | Ministry of Education — School Directory + Student Enrolments | Need school name/type/region/decile to join sport census data to geography. Enrolments give ethnic demographic context per school. | educationcounts.govt.nz → Statistics → Schooling → download School Directory CSV and Student Numbers CSV | CSV | 🔴 Critical

## Summary Dashboard
NZ Sports Data — Progress Summary (auto-calculated)
Update statuses in the Tracker sheet — this dashboard refreshes automatically.
Metric | Count | % of Total
Total Sources | 27
✅ Completed | 5 | 18.52%
⏳ In Progress | 0 | 0%
🔲 Not Started | 8 | 29.63%
🚫 Blocked | 13 | 48.15%
⚠ Incomplete | 1 | 3.704%
🆕 New (needs action) | 7 | 25.93%
Breakdown by Category
Category | Total | Completed | In Progress | Not Started | Blocked | ⚠ Incomplete | % Done
Participation | 6 | 2 | 0 | 1 | 2 | 1 | 33.33%
Govt Open Data | 8 | 2 | 0 | 3 | 3 | 0 | 25%
Rugby | 4 | 1 | 0 | 1 | 2 | 0 | 25%
Cricket | 3 | 0 | 0 | 0 | 3 | 0 | 0%
Football | 3 | 0 | 0 | 0 | 3 | 0 | 0%
Schools | 3 | 0 | 0 | 3 | 0 | 0 | 0%

## Legend & Instructions
How to use this tracker
STATUS VALUES
Completed | Data fully downloaded, cleaned, and loaded into your pipeline/DB
In Progress | Currently accessing, downloading, or integrating this source
Not Started | Haven't started yet — still to do
Blocked | Something preventing progress — check 'Action / Fix' column
⚠ Incomplete | Status was marked Complete but notes show it's actually not fully done
PRIORITY VALUES
High | Core dataset — needed to replicate the Sport NZ Insights Tool
Medium | Useful supplement — adds depth once high-priority items are done
Low | Nice to have — explore after everything else is in place
CATEGORY COLOUR CODES
Participation | Sport NZ Active NZ survey & participation data
Govt Open Data | data.govt.nz, Stats NZ, Ministry of Health
Rugby | All Blacks, Super Rugby, provincial rugby
Cricket | NZ Black Caps, Super Smash, Plunket Shield
Football | All Whites, Football Ferns, Wellington Phoenix, NZ domestic
Schools | MoE school data, School Sport NZ Census — NEW category added